## Campaign Stages and Steps
1Planet4All Climate Action Campaign | Set a Deadline | Responsibility | Record finding/notes
Stage 1: Getting started!
Step 1: Assemble a team and Brainstorm (meeting 1)
Get friends, family or peers who are passionate about taking climate action commit to campaign
Set up a planning meeting to discuss important issues and individual areas of interest
Brainstorm 1-3 climate change focus areas and ideas for action (take notes!)
Step 2: Select your topic and assign team roles (meeting 2)
Determine the climate change issue most important and realistic for the group to take action on!
Assign team roles and responsibilites e.g. Campaign Manager, Communications Manager, Events Manager, Researcher etc.
Write your mission statement
Plan ahead! Look at the remaining campaign stages/steps and set up future meetings and assign responsibilites
Stage 2: Become an Expert!
Step 1: Gather information
Research as much information about you issue as possible. Use our Speak Act Now guide for research steps (tab 3)
Determine the campaigns primary question, goal, and community you'd like to focs on
Discover what's already being done (locally or globally) to raise awareness about your issue
Identify organisations, local officials, decision makers and individuals who may have power/influence either
Step 2: Conduct Primary Research
Consider what additional information is needed or would be beneficial after your research
Reach out to the people in power you identified or individuals in your community to get more info, testimonials or opinions
Use our 'Conduct a Survey 'and I'nterview Tips' tools (tab 3) to guide you
Step 3: Synthesise Results and Refine your Mission Statement
Do you need to adjust your focus or did you discover a new issue you want people to be aware of?
Stage 3: Create your Campaign
Step 1. Determine Campaign Tools and Activities
List the tools you will use and activities the team will undertake to spread the message? Use our 'Campaign Activities' doc for inspiration (tab 3)
Map out your activity timeline (tab 2)
Decide on how you will promote/advertise your campaign and message. Check out our social assset bundle (tab 3)
Step 2: Design and Prepare Materials
Decide on a name for you campaign
Create a logo and campaign slogan
Create a hashtag
Design other materials based off of your campaign activities e.g. brochure, posters, etc.
Step 4: Launch your Campaign!
Step 1: Schedule and prepare for events, meetings etc.
Revisit your team roles. Make sure you have someone in place keeping track of all activiites & deadlines!
Step 2: Track your progress and Reflect!
Take note of what types of people and how many are engaging with your campaign
Revisit your campaign plan and decide if anything needs to be revised
Repeat the campaign cycle - keep your action going!

## Activity Timeline
Fill in the table below with your team's campaign actvity goals! Use the Campaign Activity Ideas resource in tab 3 for inspiration!
Activity Idea | Steps | Promote it | Location | Date | Details (e.g. what will you do specifically?) | Materials Needed
e.g. create a video advert - awareness raising/call to action | 1. Come up with a video concept 2. Script & Storyboard video idea 3. Record and edit | 1. Stream on campaign social channels: Instagram, Facebook, Twitter 2. Email to organisations XXX | Online
e.g. Host a Parent/Teacher Information Day | 1. Create an info brochure and slideshow presentation 2. Invite a guest speaker | 1. Ask teachers/school principal to send an email or letter home to all parents 2. Put up posters around the school with details | School

## Resources and Templates
Use the resources below to guide you in your research and campaign planning!
Speak Act Do Research Guide
Conduct a Survey
Writing a Press Release
Campaign Activity Ideas
1Planet4All Social Assest Bundle